## Dashboard
WizAccountant / WizGate — Project Dashboard
Last updated: 2026-06-30T22:00:00+03:00 ¦ Developer: Varun ¦ PM: Claude
Total Tasks | Completed | In Progress | Blocked | Est. Hours | Hours Used | Hours Left
23 | 0 | 1 | 1 | 34.5 hrs | 3.0 hrs | 31.5 hrs
[7 empty] | Completed | 0
[7 empty] | In Progress | 1
[7 empty] | Blocked | 1
[7 empty] | Pending QA | 0
[7 empty] | Not Started | 21
[7 empty] | Date | Remaining | Target
[7 empty] | 2026-06-30 | 31.5 | 34.5

## Tasks
Task Status Board
# | Task Name | Block | Est Hrs | Hrs Used | Overrun % | Status | Delay | Clock Started | Est Completion | Billing Status | Notes
8 | Schema probe queries + connector metadata | BLOCK 1 | 0.5 | 3 | 500% | In Progress | Overdue | 2026-06-30 | 2026-06-30 +0.5h | Pending PJ Approval |  | #8 | 0.5 | 3
11 | RBAC v2 — fine-grained role model + middleware | BLOCK 1 | 1 | 0 | — | Blocked | Overdue | 2026-06-30 | 2026-06-30 +1.0h | Within Estimate |  | #11 | 1 | 0
12 | Practice mode — FirmRecord + multi-site | BLOCK 2 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #12 | 1 | 0
13 | Monitoring — site SLA + failed-job alerts | BLOCK 2 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #13 | 1 | 0
14 | Mobile Phase 4 — practice + inventory + tablet | BLOCK 2 | 1.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #14 | 1.5 | 0
15 | Multi-company connector support | BLOCK 3 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #15 | 1 | 0
16 | Inventory write — warehouse transfer, credit note, RTS | BLOCK 3 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #16 | 1 | 0
17 | Order processing — SO/PO lifecycle | BLOCK 3 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #17 | 1 | 0
18 | SSO — Azure AD / Google OIDC | BLOCK 4 | 1.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #18 | 1.5 | 0
19 | Billing hooks + compliance + app store pipeline | BLOCK 4 | 1.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #19 | 1.5 | 0
20 | Stock Take — list sessions, post adjustments | BLOCK 3 | 0.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #20 | 0.5 | 0
21 | Fixed Assets (minimal) — list, get, depreciation | BLOCK 4 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #21 | 1 | 0
22 | Bank Reconciliation — statements, reconcile | BLOCK 4 | 1.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #22 | 1.5 | 0
23 | Reports — Customer (aged debtors, statement, ledger) | BLOCK 4 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #23 | 1 | 0
24 | Reports — Vendor (aged creditors, statement, ledger) | BLOCK 4 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #24 | 1 | 0
25 | Reports — Inventory (levels, movement, valuation) | BLOCK 4 | 1 | 0 | — | Not Started | On Track | — | — | Not Started |  | #25 | 1 | 0
26 | Reports — Stock Take variance | BLOCK 4 | 0.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #26 | 0.5 | 0
27 | Reports — Financial (TB, Balance Sheet, P&L) | BLOCK 4 | 2 | 0 | — | Not Started | On Track | — | — | Not Started |  | #27 | 2 | 0
28 | SaaS module — plans, onboarding, billing | BLOCK 5 | 3 | 0 | — | Not Started | On Track | — | — | Not Started |  | #28 | 3 | 0
29 | Multi-tenancy (full) — isolation, admin portal | BLOCK 5 | 2.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #29 | 2.5 | 0
30 | User Rights — role UI + permission matrix | BLOCK 5 | 1.5 | 0 | — | Not Started | On Track | — | — | Not Started |  | #30 | 1.5 | 0
31 | E-commerce — Shopify / WooCommerce | BLOCK 6 | 4 | 0 | — | Not Started | On Track | — | — | Not Started |  | #31 | 4 | 0
32 | Import — QuickBooks Online + Tally | BLOCK 6 | 4 | 0 | — | Not Started | On Track | — | — | Not Started |  | #32 | 4 | 0

## Billing
Billing Tracker
Date | Task # | Task Name | Est Hrs | Hrs Logged | Overrun Hrs | Overrun % | 120% Threshold | Approval Status | Notes
2026-06-30 | 8 | Schema probe queries + connector metadata | 0.5 | 3 | 2.5 | 500% | 0.6 | Pending PJ Approval

## Burndown Data
Date | Hours Remaining | Target Remaining
2026-06-30 | 31.5 | 34.5