## Overview
Field | Value
Product | WizAccountant — Plan 1
Architecture | On-prem WizConnector (.NET + Sage Evolution SDK) ↔ Cloud WizAccountant (Web + API)
Transport | Outbound HTTPS / WebSocket (no WizVPN, no SSH)
System of record | Client Sage 200 Evolution on LAN (unchanged)
Mobile | iOS + Android — same cloud API as web; no Sage SDK on device
Mobile stack (recommended) | React Native or Flutter; FCM + APNs for push
Last updated | 2026-05-26
Principles
Allowlisted operations only (no raw SDK/SQL from UI or AI)
Reads before writes; writes need audit + approval from Phase 3
Every job: jobId, tenantId, siteId; idempotencyKey for posts
UI shows site online/offline and Sage company name

## Phase 1 Checklist
Done | ID | Component | Task | Status
☑ | P1-01 | Solution | Create WizAccountant.slnx + Contracts, Api, Connector projects | Complete
☑ | P1-02 | Contracts | Shared DTOs: pairing, site, job, heartbeat, run-job message | Complete
☑ | P1-03 | API | SQLite persistence (sites, pairing codes, jobs) | Complete
☑ | P1-04 | API | POST /api/pairing-codes — generate pairing code | Complete
☑ | P1-05 | API | POST /api/sites/pair — register connector site | Complete
☑ | P1-06 | API | GET /api/sites — list sites + online status | Complete
☑ | P1-07 | API | POST/GET /api/jobs — submit job, poll result | Complete
☑ | P1-08 | API | SignalR Connector Hub — register, heartbeat, route RunJob | Complete
☑ | P1-09 | Connector | Worker service: pair on first run, save site state | Complete
☑ | P1-10 | Connector | Connect to hub, register site, 30s heartbeat loop | Complete
☑ | P1-11 | Connector | Receive RunJob, execute handler, POST job result | Complete
☑ | P1-12 | Connector | Job shell: Site.Health (mock) | Complete
☑ | P1-13 | Connector | Job shell: Customer.List (mock) | Complete
☑ | P1-14 | Build | dotnet build WizAccountant.slnx succeeds | Complete
☑ | P1-15 | Connector | Wire Pastel.Evolution SDK — Site.Health (live DB) | Complete
☑ | P1-16 | Connector | SDK handler: GLAccount.List + GLAccount.Get | Complete
☑ | P1-17 | Connector | SDK handler: Customer.List + Customer.Get | Complete
☑ | P1-18 | Connector | SDK handler: CustomerTransaction.List (criteria) | Complete
☑ | P1-19 | Connector | SDK handler: Supplier.List + SupplierTransaction.List | Complete
☑ | P1-20 | Connector | Evolution connection profile + Agent.Authenticate (WizConnector.Setup + DPAPI) | Complete
☑ | P1-21 | Connector | WizConnector.Tray — pairing wizard, status, device ID | Complete
☑ | P1-22 | API | Auth stub — tenants + users (minimal) | Complete
☑ | P1-23 | Web | Admin UI — create pairing code, list sites, Test connection | Complete
☑ | P1-24 | API | Job wait/poll helper — sync read with timeout (30–60s) | Complete
☑ | P1-25 | API | Basic audit log table for all jobs | Complete
☑ | P1-26 | Connector | REST long-poll fallback when WebSocket down | Complete
☑ | P1-27 | Docs | Sage connection runbook (DOCS/SAGE-Connection-Process.md); version matrix TBD | Complete
☑ | P1-28 | Pilot | End-to-end test on pilot site #1 (pair → online → Customer.List) | Complete
☑ | P1-29 | Pilot | End-to-end test on pilot site #2 (second Evolution version) | Complete
☑ | P1-30 | Success | Site Online within 60s of connector start | Complete
Summary |  |  | 30 / 30 complete

## Phase 2 Checklist
Done | ID | Component | Task | Status
☑ | P2-01 | Connector | Expanded SDK reads (GL tx, orders, inventory, master data) | Complete
☑ | P2-02 | Connector | AR/AP open items handlers | Complete
☑ | P2-03 | Connector | Criteria builder (date, account, reference) + pagination | Complete
☑ | P2-04 | Connector | site.diagnostics support bundle | Complete
☑ | P2-05 | Connector | dashboard.summary + search.global | Complete
☑ | P2-06 | API | Insight dashboard + search endpoints | Complete
☑ | P2-07 | API | Read-only AI chat + conversation history | Complete
☑ | P2-08 | API | CSV export from job results | Complete
☑ | P2-09 | API | Notification email stub + log | Complete
☑ | P2-10 | API | Per-site rate limiting | Complete
☑ | P2-11 | API | API versioning /api/v1/insight/tools | Complete
☑ | P2-12 | Web | Insight UI — dashboard, AR/AP, search, chat | Complete
☑ | P2-13 | Docs | PHASE2-AI-GUARDRAILS.md | Complete
☑ | P2-14 | Mobile | Native iOS/Android app (Expo — mobile/wiz-accountant) | Complete
☐ | P2-15 | Cloud | Production JWT + Brevo email integration | NEXT
☐ | P2-16 | Connector | Signed auto-update channel | Pending
Summary |  |  | 14 / 16 complete

## Phase 3 Checklist
Done | ID | Component | Task | Status
☑ | P3-01 | Connector | Idempotency store (SQLite) | Complete
☑ | P3-02 | Connector | Write handlers GL/AR/AP + master save | Complete
☑ | P3-03 | Connector | Sage transactions BeginTran/Commit + error mapping | Complete
☑ | P3-04 | Connector | Write consent store (Tray-ready) | Complete
☑ | P3-05 | API | Approval queue propose/approve/reject | Complete
☑ | P3-06 | API | Maker-checker roles (Preparer vs Approver) | Complete
☑ | P3-07 | API | AI propose draft (structured JSON) | Complete
☑ | P3-08 | API | Write audit before/after + Evolution ref | Complete
☑ | P3-09 | API | Workflow templates + site config sync | Complete
☑ | P3-10 | Web | Act UI — inbox, propose, audit | Complete
☑ | P3-11 | Docs | PHASE3-APPROVALS.md + rollback messaging | Complete
☑ | P3-12 | Mobile | Approval inbox native app (Approvals tab) | Complete
☑ | P3-13 | Connector | Tray consent menu item | Complete
13 / 13 complete

## Phase Summary
Phase | Name | Release | Duration | Goal | Writes | AI | Mobile
1 | Connect & read | v0.1 Connect | 8–12 weeks | Pairing, live reads, site online | No | No | No app — API mobile-ready
2 | Insight | v0.5 Insight | 8–12 weeks after P1 | Web workspaces + read-only AI | No | Read-only tools | iOS/Android read + push
3 | Act | v1.0 Act | 12–16 weeks after P2 | Approvals + posting to live Sage | Yes (gated) | Propose → approve | Approval inbox + push
4 | Scale | v1.x Scale | Ongoing after P3 | Inventory, orders, enterprise | Expanded | Workflows | Practice mode, tablet, store release

## Features
Phase | Component | Area | Feature | Details | Read/Write
1 | WizConnector | Platform | Windows Service | Auto-start, recovery, structured logging | Read
1 | WizConnector | Platform | System tray app | Pairing wizard, connection status, device/site ID, open logs | Read
1 | WizConnector | Platform | Pairing | One-time code from cloud → store siteId + credentials (DPAPI) | Read
1 | WizConnector | Platform | Cloud link | Outbound TLS; WebSocket/SignalR + REST fallback long-poll | Read
1 | WizConnector | Platform | Heartbeat | Every 30–60s; version, SDK/Evolution version, company DB name | Read
1 | WizConnector | Platform | Local config | Evolution connection profile, SDK agent user (encrypted) | Read
1 | WizConnector | Platform | Health handler | Site.Health — DB reachable, SDK auth OK | Read
1 | WizConnector | Sage SDK | GL | GLAccount.List, GLAccount.Get | Read
1 | WizConnector | Sage SDK | AR | Customer.List, Customer.Get, CustomerTransaction.List | Read
1 | WizConnector | Sage SDK | AP | Supplier.List, Supplier.Get, SupplierTransaction.List | Read
1 | WizConnector | Sage SDK | Reports | Trial balance–style extracts (scoped queries) | Read
1 | WizConnector | Sage SDK | Inventory (optional) | InventoryItem.List, InventoryItem.Get | Read
1 | WizAccountant Cloud | Platform | Auth | Email/password or SSO stub; tenants + users | Read
1 | WizAccountant Cloud | Platform | Sites | Register tenant → pairing code → list sites, last seen | Read
1 | WizAccountant Cloud | Platform | Connector Hub | Route jobs to siteId; job queue + timeout | Read
1 | WizAccountant Cloud | Platform | Admin UI | Sites list, connection status, Test connection | Read
1 | WizAccountant Cloud | Platform | Job API | Submit job → wait/poll result (sync read 30–60s cap) | Read
1 | WizAccountant Cloud | Platform | Audit (basic) | Log job type, user, site, timestamp, success/fail | Read
2 | WizConnector | Platform | Expanded reads | Outstanding balances, aged analysis, detail by Autoidx | Read
2 | WizConnector | Platform | Search / filter | Criteria builders: account, date range, reference | Read
2 | WizConnector | Platform | Performance | Connection pooling, timeouts, pagination | Read
2 | WizConnector | Platform | Diagnostics | Support bundle: redacted logs, versions, last 50 jobs | Read
2 | WizConnector | Platform | Auto-update (optional) | Signed installer check channel | Read
2 | WizConnector | Sage SDK | AR | Open items/outstanding; allocations read | Read
2 | WizConnector | Sage SDK | AP | Same for suppliers | Read
2 | WizConnector | Sage SDK | GL | Transaction list by account/period | Read
2 | WizConnector | Sage SDK | Inventory | Stock levels, item search | Read
2 | WizConnector | Sage SDK | Orders | SalesOrder.List, PurchaseOrder.List | Read
2 | WizConnector | Sage SDK | Master data | Projects, warehouses, tax rates, transaction codes list | Read
2 | WizAccountant Cloud | Platform | Dashboard | TB summary, debtors/creditors KPIs | Read
2 | WizAccountant Cloud | Platform | AR/AP workspaces | Browse customers/suppliers, drill to transactions | Read
2 | WizAccountant Cloud | Platform | Global search | Cross-entity search | Read
2 | WizAccountant Cloud | Platform | AI chat (read-only) | Tools = read handlers; citations | Read
2 | WizAccountant Cloud | Platform | Conversation history | Per tenant/user | Read
2 | WizAccountant Cloud | Platform | Export | CSV/PDF for visible lists | Read
2 | WizAccountant Cloud | Platform | Notifications | Email: invites, site offline (e.g. Brevo) | Read
2 | WizAccountant Cloud | AI Guardrails | Tool allowlist | Read handlers only | Read
2 | WizAccountant Cloud | AI Guardrails | System prompt | Never claim posted; suggest approval for actions | Read
2 | WizAccountant Cloud | AI Guardrails | Data timestamp | Show data as of job completion | Read
2 | WizAccountant Mobile | iOS / Android | Auth | Login, biometric unlock, secure token storage | Read
2 | WizAccountant Mobile | iOS / Android | Sites | List sites, online/offline, switch tenant/site | Read
2 | WizAccountant Mobile | iOS / Android | Dashboard | Debtors/creditors totals, TB snapshot (read-only) | Read
2 | WizAccountant Mobile | iOS / Android | AR/AP quick view | Customer/supplier search, open items | Read
2 | WizAccountant Mobile | iOS / Android | Push notifications | Site offline alert; optional daily summary | Read
2 | WizAccountant Mobile | iOS / Android | AI chat (read-only) | Same tools as web; mobile UI | Read
2 | WizAccountant Mobile | iOS / Android | Deep links | Open entity from notification | Read
3 | WizConnector | Platform | Idempotency store | Local SQLite: idempotencyKey → result hash | Write
3 | WizConnector | Platform | Write handlers | Allowlisted post operations | Write
3 | WizConnector | Platform | Transactions | BeginTran / Commit / Rollback per action | Write
3 | WizConnector | Platform | StartNewBatch | Separate audit batches per post | Write
3 | WizConnector | Platform | Error mapping | Evolution exceptions → stable error codes | Write
3 | WizConnector | Platform | Consent (optional) | Tray: Allow cloud to post for 1 hour | Write
3 | WizConnector | Sage SDK | GL | GLTransaction.Post; journal batch create only — VAT legs per SDK | Write
3 | WizConnector | Sage SDK | AR | CustomerTransaction.Post; Allocations.Save — Codes per site config | Write
3 | WizConnector | Sage SDK | AP | SupplierTransaction.Post; Allocations.Save — Codes per site config | Write
3 | WizConnector | Sage SDK | Master (limited) | Customer.Save, Supplier.Save — Role-gated | Write
3 | WizConnector | Sage SDK | Orders (optional 3b) | SalesOrder/PurchaseOrder Save + Process partial — Sub-phase | Write
3 | WizAccountant Cloud | Platform | Approval queue | Proposed journal/payment → approver → execute | Write
3 | WizAccountant Cloud | Platform | Maker-checker | Prepare vs approve roles | Write
3 | WizAccountant Cloud | Platform | AI propose, human approve | Draft only until approved | Write
3 | WizAccountant Cloud | Platform | Write audit | Before/after, user, approver, Evolution ref | Write
3 | WizAccountant Cloud | Platform | Workflows (starter) | Month-end checklist, payment run proposal | Write
3 | WizAccountant Cloud | Platform | Site config sync | Transaction codes, tax, branch | Write
3 | WizAccountant Cloud | Platform | Rollback messaging | Posts not auto-reversed in product | Write
3 | WizAccountant Mobile | iOS / Android | Approval inbox | Pending journals, payments, allocations | Write
3 | WizAccountant Mobile | iOS / Android | Approve / reject | Maker-checker with comment | Write
3 | WizAccountant Mobile | iOS / Android | Push notifications | Approval required + deep link | Write
3 | WizAccountant Mobile | iOS / Android | AI drafts | View proposal; approve via flow | Write
3 | WizAccountant Mobile | iOS / Android | Audit (read) | Approval history per item | Write
4 | WizConnector | Platform | Multi-company | One agent → multiple company DBs | Write
4 | WizConnector | Platform | Branch context | SetBranchContext per site | Write
4 | WizConnector | Platform | Heavy modules | CN, RTS, inventory adj, warehouse transfer | Write
4 | WizConnector | Platform | Order processing | SO/PO Process, partial, Complete | Write
4 | WizConnector | Platform | Offline queue (optional) | Buffer approved jobs when Sage busy | Write
4 | WizAccountant Cloud | Platform | Practice mode | One firm, many client sites | Read
4 | WizAccountant Cloud | Platform | RBAC | Read vs propose vs approve vs admin | Read
4 | WizAccountant Cloud | Platform | SSO | Azure AD / Google | Read
4 | WizAccountant Cloud | Platform | Monitoring | Site SLA, failed job alerts | Read
4 | WizAccountant Cloud | Platform | Billing | Per site / per user hooks | Read
4 | WizAccountant Cloud | Platform | Compliance | DPA templates, retention | Read
4 | WizAccountant Cloud | Platform | Advanced AI | Multi-step workflows; doc upload draft | Read
4 | WizConnector | Sage SDK | Inventory | InventoryTransaction.Post; CN/RTS Process; warehouse | Write
4 | WizConnector | Sage SDK | Orders | Full SO/PO lifecycle | Write
4 | WizConnector | Sage SDK | CRM | Incidents (if needed) | Write
4 | WizConnector | Sage SDK | Job costing | Job card Save only (no process) | Write
4 | WizAccountant Mobile | iOS / Android | Practice mode | Switch client site for accounting firms | Read
4 | WizAccountant Mobile | iOS / Android | Inventory (read) | Stock lookup, low-stock push alert | Read
4 | WizAccountant Mobile | iOS / Android | Workflows | Starter checklist steps from phone | Read
4 | WizAccountant Mobile | iOS / Android | Tablet layout | iPad / Android tablet for approvers | Read
4 | WizAccountant Mobile | iOS / Android | App store release | Production signing, crash analytics, staged rollout | Read
1 | WizAccountant Cloud | Platform | API mobile-ready | JWT, same job endpoints — no native app in P1 | Read

## Success Criteria
Phase | Success criterion
1 | Pair reads on 2 pilot sites (Evolution versions documented)
1 | Site Online within 60s of service start
1 | Read customer list + AR open items without desktop Sage
1 | No inbound ports on customer firewall
2 | Natural language → correct AR/AP answer on pilot data
2 | 5 read tools in chat with >99% success rate
2 | Accountants prefer browser for enquiry vs Evolution
2 | Mobile: login, dashboard, one AR enquiry on iOS or Android
3 | GL journal: propose → approve → balanced post in live Sage
3 | Duplicate idempotency key does not double-post
3 | Allocation payment to invoice on pilot AR
3 | Full audit trail export for one transaction
3 | Mobile: approver completes one payment from push notification
4 | 20+ sites under management with monitoring
4 | At least one inventory workflow in production
4 | Enterprise pilot with SSO + practice multi-site

## Platform (Cross-Phase)
Capability | Phase introduced
Shared contracts NuGet (JobRequest / JobResult) | 1
PostgreSQL (tenants, sites, jobs, audit) | 1
SignalR / WebSocket hub | 1
Serilog + correlation id | 1
DPAPI secrets on connector | 1
CI: connector MSI + API docker | 1
Evolution version matrix doc | 1
Rate limiting per site | 2
API versioning | 2
Push notifications (FCM / APNs) | 2
Mobile apps (iOS + Android) | 2
Mobile approval UX | 3

## Mobile Strategy
Topic | Detail
Principle | Mobile uses same WizAccountant cloud API as web — no WizConnector or Sage SDK on device
Phase 1 | No native app; ensure API auth (JWT), pagination, mobile-friendly JSON
Phase 2 | Ship iOS + Android: read-only parity with key web screens + push
Phase 3 | Approval inbox — primary mobile value for managers on the go
Phase 4 | Practice multi-site, tablet UX, app store hardening
Recommended stack | React Native or Flutter (one codebase); alternatively .NET MAUI if team is C#-only
Push | Firebase Cloud Messaging (Android) + Apple Push Notification service
Security | Biometric unlock, short-lived tokens, certificate pinning (enterprise option)
Out of scope | Offline posting to Sage; full Evolution parity on mobile

## Sage Module Priority
Priority | Module | Phases | Notes
1 | GL | 1–3 | Accounts, journals
2 | AR / AP | 1–3 | Masters, transactions, allocations
3 | Inventory | 2 read, 4 write | Items, adjustments
4 | Sales / Purchase orders | 3b / 4 | High complexity
5 | CRM / Job costing | 4+ | Niche; job card no process via SDK

## Not Building (Plan 1)
Item
WizVPN / network tunnel to LAN
Hosted customer DB restore as primary product
Full cloud replacement of Evolution UI (Plan 3)
Raw SQL access from web or AI
Evolution report printing via SDK
Unrestricted SDK passthrough
Cashbook / journal batch process via SDK
Job card process/complete via SDK

## Phase 1 Exclusions
Excluded from Phase 1
AI chat
Workflows
Writes to ledger
Multi-site analytics
Native mobile app (API only in P1)
Inventory documents
Orders Process()
Allocations

## SDK Limits (Phase 3+)
Limitation | Notes
Cashbook / journal batch process | SDK cannot process — create only
Job card process/complete | Not supported by SDK
Evolution printing | Not available in SDK

## Execution Status
Status | Work item | Component | Updated (UTC)
Done | P1-01: Create WizAccountant.slnx + Contracts, Api, Connector projects | Solution | 2026-05-26
Done | P1-02: Shared DTOs: pairing, site, job, heartbeat, run-job message | Contracts | 2026-05-26
Done | P1-03: SQLite persistence (sites, pairing codes, jobs) | API | 2026-05-26
Done | P1-04: POST /api/pairing-codes — generate pairing code | API | 2026-05-26
Done | P1-05: POST /api/sites/pair — register connector site | API | 2026-05-26
Done | P1-06: GET /api/sites — list sites + online status | API | 2026-05-26
Done | P1-07: POST/GET /api/jobs — submit job, poll result | API | 2026-05-26
Done | P1-08: SignalR Connector Hub — register, heartbeat, route RunJob | API | 2026-05-26
Done | P1-09: Worker service: pair on first run, save site state | Connector | 2026-05-26
Done | P1-10: Connect to hub, register site, 30s heartbeat loop | Connector | 2026-05-26
Done | P1-11: Receive RunJob, execute handler, POST job result | Connector | 2026-05-26
Done | P1-12: Job shell: Site.Health (mock) | Connector | 2026-05-26
Done | P1-13: Job shell: Customer.List (mock) | Connector | 2026-05-26
Done | P1-14: dotnet build WizAccountant.slnx succeeds | Build | 2026-05-26
Done | P1-15: Wire Pastel.Evolution SDK — Site.Health (live DB) | Connector | 2026-05-26
Done | P1-16: SDK handler: GLAccount.List + GLAccount.Get | Connector | 2026-05-26
Done | P1-17: SDK handler: Customer.List + Customer.Get | Connector | 2026-05-26
Done | P1-18: SDK handler: CustomerTransaction.List (criteria) | Connector | 2026-05-26
Done | P1-19: SDK handler: Supplier.List + SupplierTransaction.List | Connector | 2026-05-26
Done | P1-20: Evolution connection profile + Agent.Authenticate (WizConnector.Setup + DPAPI) | Connector | 2026-05-26
Done | P1-21: WizConnector.Tray — pairing wizard, status, device ID | Connector | 2026-05-26
Done | P1-22: Auth stub — tenants + users (minimal) | API | 2026-05-26
Done | P1-23: Admin UI — create pairing code, list sites, Test connection | Web | 2026-05-26
Done | P1-24: Job wait/poll helper — sync read with timeout (30–60s) | API | 2026-05-26
Done | P1-25: Basic audit log table for all jobs | API | 2026-05-26
Done | P1-26: REST long-poll fallback when WebSocket down | Connector | 2026-05-26
Done | P1-27: Sage connection runbook (DOCS/SAGE-Connection-Process.md); version matrix TBD | Docs | 2026-05-26
Done | P1-28: End-to-end test on pilot site #1 (pair → online → Customer.List) | Pilot | 2026-05-26
Done | P1-29: End-to-end test on pilot site #2 (second Evolution version) | Pilot | 2026-05-26
Done | P1-30: Site Online within 60s of connector start | Success | 2026-05-26